## Assignments
Modular Decompression System Project Assignments
Updated: | 19.08.2011
Model / IP / TB | Assignments | Responsibility | Synthised Already | Start Date | Done Date / Expected | Status
UART TX&RX Generator |  | Beeri | --- | 16.11.2010 | 16.12.2010 | DONE
UART RX | Delete HALFBIT_ST State, by counting until the middle of the bit | Alon | YES | 17.11.2010 | 22.12.2010 | DONE
| Add value of '5' to sample_cnt at IDLE_ST, when STARTBIT is identified | Alon | YES | 6.1.2011 | 8.1.2011 | DONE
| Parity error flag does not rise. Fix bug | Alon | No | 4.4.2011 | 7.4.2011 | OPEN (Not updated in SVN)
| Fix drifting problem (2 stop bits are needed by Matlab to send correct value) | Alon | YES | 22.12.2010 | 13.3.2011 | DONE
UART TX | dout_i should be implemented more efficient (Shift Register) | Alon | YES | 12.02.2011 | 5.3.2011 | DONE
| Add 'data_valid' port from FIFO | Alon |  | 24.12.2010 | 1.1.2011 | DONE
| Check if missing stop bit at special FIFO situation | Beeri |  | 6.1.2011 | 14.1.2011 | DONE
| dout_i should be implemented more efficient (Shift Register) | Alon |  | 1.1.2011 | 22.02.2011 | DONE
| Use ShiftRegister | Alon |  | 24.12.2010 | 1.1.2011 | DONE
| Use external FIFO | Alon |  | 27.11.2010 | 20.12.2010 | DONE
UART TB | Add many test to the regression | Alon | --- | 27.11.2010 | 25.3.2011 | DONE
MessagePack Decoder | CRC - Change interface. WHEN waste too many logic | Beeri | YES | 19.11.2010 | 22.12.2010 | DONE
| Remove CRC output port | Beeri |  |  | 22.12.2010 | DONE
| Change blk_pos range to automatic function | Beeri |  |  | 7.2.2011 | DONE
| Change blocks to Shift Registers | Beeri |  |  | 7.2.2011 | DONE
| Add SR to support special problematic SOF words | Beeri |  |  | 17.1.2011 | DONE
| init_sof_eof_proc : See how it looks like after synthesis, then consult about it with Moshe | Beeri |  |  | 22.12.2010 | DONE
MessagePack Encoder | init_sof_eof_proc : See how it looks like after synthesis, then consult about it with Moshe | Beeri | YES | 27.11.2010 | 19.12.2010 | DONE
| Change blk_pos range to automatic function | Beeri |  |  | 07.2.2011 | Open
| Fix CRC Process | Beeri |  |  | 27.12.2011 | DONE
| Replace UART interface with FIFO interface | Beeri |  |  | 20.12.2010 | DONE
UART&MP TB | Add Regresion to Macro File | Beeri | --- | 20.12.2010 | 1.1.2011 | Deleted. Done manually
| Re-run after UART and MP changes | Beeri | --- | 20.11.2010 | 22.12.2010 | DONE
RAM Simple | Add Synplify attributes | Beeri |  | 2.6.2011 |  | Deleted. Re-used in VLSI Lab, with different synthisizer
| Write one | Beeri | YES | 8.12.2010 | 16.12.2010 | DONE
Ram Generic | Add Input > Output implementation | Beeri | YES | 8.12.2010 | 24.3.2011 | DONE
RAM TB | Check why power2_out_g is not working when greater than 2 | Beeri | --- | 15.12.2010 | 13.08.2011 | Done (Works fine when using RAM new package)
| Check why power2_out_g is not working when greater than 2 | Beeri | --- | 15.12.2010 | 13.08.2011 | Done (Works fine when using RAM new package)
Generic Decoder |  | Beeri | YES | 14.12.2010 | 16.12.2010 | DONE
Generic MUX | Add comments, Upgrade code | Beeri | YES | 14.12.2010 | 1.1.2011 | DONE
| Change output port to support more than 1 std_logic_vector | Beeri |  |  | 1.1.2011 | DONE
General FIFO | Add Synplify attributes | Beeri |  | 2.6.2011 |  | Deleted. Re-used in VLSI Lab, with different synthisizer
| Change generic log to use 'log' function | Beeri | YES | 26.12.2010 | 1.1.2011 | OPEN
| Check if 'used' is missing one bit | Beeri |  | 21.12.2010 | 24.12.2011 | DONE
CheckSum | Fix calculation bug (Problem was in MP_Enc Reset) | Beeri | YES | 7.1.2011 | 10.1.2011 | DONE
VESA Generic Controller | Write Vesa Generator Controller | Beeri | No | 13.1.2011 | 13.03.2011 | DONE
| Image generator and collector : Add function to read input files and write output files | Beeri | --- | 07.02.2011 | 17.02.2011 | Deleted (Using BMP_IO_PACKAGE)
Debouncer | Change Debouncer, according to Moshe's sample | Beeri | Yes | 7.2.2011 | 28.02.2011 | DONE
PLL & Top clock TB | Upgrade | Beeri | --- | 7.2.2011 | 7.3.2011 | DONE
RX Block | Separate Wishbone Master from RX block to individual entity | Alon |  | 2.6.2011 | 1.7.2011 | Open
| Gather UART_RX, MP_DEC, CheckSum and RAM to 1 block (1 component) | Alon | Yes | 25.3.2011 | 1.4.2011 | Done
| Add Wishbone Master signals & FSM to RX Block | Alon | Yes | 25.3.2011 | 28.5.2011 | Done
TX Block | Gather UART_TX, MP_ENC, CheckSum, FIFO and RAM to 1 block (1 component) | Alon | Yes | 25.3.2011 | 1.4.2011 | Done
| Add Wishbone Master and Slage signals & FSM to TX Block | Alon |  | 25.3.2011 | 14.5.2011 | Open
Wishbone INTERCON | Implement INTERCON | Beeri | Yes | 31.5.2011 | 13.08.2011 | Closed
| Connect INTERCON X, INTERCON Y | Alon |  | 13.08.2011 |  | Open
Memory Control Read | Write one | Beeri | Yes | 25.3.2011 | 8.5.2011 | Done
Memory Control Write | Write one | Beeri | Yes | 25.3.2011 | 14.4.2011 | Done
Memory Arbiter | Write one | Beeri | Yes | 25.3.2011 | 14.4.2011 | Done
Pixel Manager | Write one | Beeri | Yes | 25.3.2011 | 15.5.2011 | Open
SDRAM Controller | Upgrade - Add Wishbone Slave, and run with TB | Beeri | Yes | 25.3.2011 | 14.4.2011 | Done
Memory Block | Gather Memory Rd, Wr and Arbiter under 1 block with Wishbone Master and Slave | Beeri | Yes | 25.3.2011 | 10.5.2011 | Done
Video Block | Synchronize registers to 40 MHz | Beeri |  | 1.6.2011 |  | Open
| Gather Pixel Manager, Dual Clock FIFO, Synthetic Image Generator, VESA generator (and runlen decompressor - optional for now) under 1 block with Wishbone Master | Beeri | Yes | 25.3.2011 | 14.5.2011 | Done
TOP Block | Connect all blocks together & run TB | Beeri | Yes | 25.3.2011 | 31.5.2011 | Done
RunLen Decompressor | Upgrade | Beeri | Yes | 10.5.2011 | 15.5.2011 | Done
MatLab Interface | Upgrade | Beeri | --- | 5.5.2011 | 21.5.2011 | Done
Report Package | Write one | Beeri |  |  | 1.1.2011 | Open
SDRAM Model | Add generics, running address in incremental burst | Beeri | --- |  | 19.8.2011 | Closed
USB Support | Add USB Support | TBD |  |  |  | Open
General Register | Upgrade | Beeri |  |  |  | Open
Generic RAM | Add Dump to and Load from file | Beeri |  |  |  | Open
FPGA Version | Add register | Beeri | --- |  |  | Optional
MegaWizard | Implement for RAM | Beeri |  |  |  | Done
… (will be added more)